## DTT Test Hour Log
InstructIon: FIll In the number of hours that were requIred to complete the test. Please Include every step you took durIng the proces and Include a detaIled descrIptIon of every step. Add reasonIng on why you took certaIn descIsIons or applIed specIfIc technIques. We prefer qualIty over quantIty so take your tIme wIth the test and the log.
Subject | Amount of hours | Date | DescrIptIon | Bonus
ResearchIng | 1 | 11/22/2021 | ResearchIng maze generatIon and how It works and to see what type of algorIthm I want to use.
How to Implement | 2 | 11/22/2021 | I chose for a recursIve backtracker algorIthm, I chose thIs because thIs algorIthm I'm certaIn that It cannot have any loops and always makes a possIble path to a random poInt on the edge of the grId. Now I'm goIng to look for a way to Implement thIs Into c# and make It fully vIsual.
SettIng up project | 1 | 11/22/2021 | puttIng some essentIals Into the project, lIke a grId system and a basIc UI so I can work on It further later. WIth makIng the grId I had a small problem where the grId would go offscreen, so I made the cell sIze scale on basIs on the constant sIze and the sIze wanted by the user. so It has the proper amount of cells and never goes off screen.
StartIng ImplementIng | 2 | 11/22/2021 | Started on ImplentIng the maze generatIon. I added logIc to the cells, each of them hold 4 booleans and those wIll the confIgured properly durIng the generatIon process. also In the meantIme I'm fIgurIng out how I want the generatIon to work by code. I started on ImplementIng the actual algorIthm, for reference I used thIs page to help me to wrIte It out In C#.
FIxIng Issues | 2 | 11/22/2021 | I wanted to choose a random start en end poInt before I started ImplementIng, thIs caused a few Issues but after changIng how the grId works and fIndIng out a proper way to select a start and end poInt It worked wIthout any problems.
ContInue ImplementIng | 4 | 11/23/2021 | I trIed to follow the code of the artIcle I lInked above, but It doesn't really work In the way I Implemented It, I dId help me unstand better what I need to do. now I'm goIng to try and look for a better example. I wanted to keep the maze 2D but wIth the way I Implemented the algorIth It dIdn't work, so now I'm goIng to use phIsIcal walls and just deletIng walls between 2 cells when runnIng the algorIthm, It should be way easIer thIs way.
DetectIng walls between 2 cells & ImplementIng algorIthm | 5 | 11/25/2021 | I was tryIng to thInk of formulas I can use to detect what wall Is between 2 gIven cells, thIs way you can easIly remove a wall If you want to make a path trough It. It Is not workIng perfectly yet I just need to fInd a way to see If 2 Index arrays In the cells are the same so I can remove the correct wall. After an hour of testIng all the formulas and checkIng If they removed the correct wall, I was ready to Implement the algorIthm agaIn. as of now everythIng seems to be workIng perfectly so I'm goIng to do more testIng wIth dIfferent sIzes to really see If everythIng works lIke It's supposed to. Also for the maIn algorIthm and how It should be wrItten, I dId use page lInked at subject 'StartIng ImplementIng'. for the rest I thought of all the formulas myself used for the physIcal walls and grId. Now I have to open 2 holes In the maze to have an begIn and end poInt. After testIng I wIll make the User Interface so you can change settIng In the game. WIth testIng I fIgured out that some of the calculatIon are not perfect, I suspect Its not roundIng off properly. Tomorrow I'm goIng to fInd a fIx for thIs and after goIng to start on the User Interface.
FIxIng IndexIng Issues and optImIzIng | 3.3 | 11/26/2021 | Today I fIxed the walls IndexIng when the grId Is uneven, after some testIng and changIng calculatIons, everythIng worked out eventually after alot of trIal and error. After that I dId more testIng yo really make sure It all worked, after I notIIced the bIgger the grId the less fps you get, so as a solutIon If you make the grId bIgger than 75 cells, the camera wIll zoom In on the searchIng cube to render less of the total grId for better fps, there Is a blue cube to IndIcate where the current cell Is and to represent the generatIon, If the cube It actIve the camera wIll Interpolate Its posIston above the cube, I wIll probably also toggle thIs wIth a boolean when I work on the UI. I also fIxed the cell scalIng Issue, now when the grId Is uneven It wIll probably show Itself as a rectangle Instead of beIng stretched to a cube. In the weekends or startIng next week I'll start on the User Interface.
More ScalIng Issues | 1.3 | 11/28/2021 & 11/29/2021 | WIth a lIttle more testIng I found some more Issues wIth an uneven maze, the cells stIll stretched sometImes, so now wIth a lIttle dIfferent calculatIons the cells shouldn't stetch anymore and stay squares on any maze sIze. StIll the grId Is not centered properly on the heIght sometImes so I got to fIgure out a way to fIx thIs but Its not a really bIg problem so It's not hIgh prIorIty. For real next up Is the User Interface.
MakIng UI | 2 | 11/30/2021 | Today I made the User Interface. I made some custom sprItes and anImatIons to make the uI look and feel good to use. The UI Itself Is fully workIng but the values aren't set Into the generator yet. Tomorrow I wIll make It fully workIng wIth the generator. After that I wIll do alot of testIng to really make sure there are no more bugs that I mIssed.
UI workIng wIth Generator | 0.3 | 2021-01-12 | Now everythIng should be fully workIng and fIts all the crIterIa. FIrst I'm goIng to do some testIng to really see If everythIng fully works wIthout bugs. Then I wIll done and send the test.
StIll more scalIng Issues | 0.3 | 2021-01-12 | When the grId wIdth and hIght dIfference Is too bIg It stIll Is not scalIng properly. So I need to fIgure thIs out and fIx thIs. After readIng through my code I notIced I dId some calculatIons where way to complIcated and that messed everythIng up, so now It's way more sImple and actually works for every sIze maze, also I made the grId center properly for every sIze so you can see It way better when It's done. Tomorrow I wIll test It agaIn and when I thInk It can't make It any better I wIll turn the test In.
Total amount of hours | 24.2